## Contents
Project Plan Contents (Click on an option to reach it)
Sheet | Description
Team & Roles | A summary of team members and their roles
Scenario | Project scenario and it's breakdown
Overview/Tech | Overview of the tech/tools used
Plan | Project plan with the backlog of user stories and details of all sprints
Schedule | An estimated schedule for the project
Requirements/ Constraints | Description of all requirements and constraints
Features List | A full list of features

## Team
Team
Name | Sub team / Role
Mohammed Mohammed Ali | Front end / Scrum Team
Alaa Obour | Front end / Scrum Team
Mohamed Ahmed | Android/ Scrum Team
Mohamed Baz | Backend / Product owner
Mohamed Nada | Backend / Deputy Scrum Master
Mohamed Ali Farouk | Backend/ Android / Scrum Master

## Scenario
Scenario | Break down
Thoughts is a micro-blogging platform(Like twitter). We call a micro-blog(thought) a "Thought". By creating an account a user can post a "Thought" to his profile. The user can also follow a friend to his shared "Thoughts". A user can reply to any Thought and also post a picture as a Thought. A user can change their settings and their password. And also send and receive private messages from friends. A signed- in user can also see a stream of "Thoughts" of people that the user is following. The user can choose a profile picture that appears next to their name. Each user has a profile with their name, profile picture, and their "Thoughts". A user can like a "Thought" and have it added to their favorites. A user can also share a link to any thought through a sharing interface. The user can use our platform (Thoughts) through their browser or through our mobile app.
| Title | Sign up | Title | Reply to a Thought
| Description | Give A visitor a form to sign-up. | Description | A user can reply to any Thought.
| Title | Sign in | Title | Update Settings
| Description | Give a current user a form to sign in. | Description | Give a user an interface to change their settings.
| Title | Home stream | Title | Forgot password
| Description | Show a stream of thoughts of people a user follows | Description | A way for the user to change their password.
| Title | User profile | Title | Post a photo
| Description | Show a user's profile, including name, picture, and Thoughts. | Description | Allow a user to post a picture as a Thought.
| Title | Profile picture | Title | Private messages
| Description | Give option to Add a personal profile picture. | Description | A allow a user to send a friend a private message.
| Title | Update about | Title | Inbox
| Description | Allow users to type a small message about them on their profiles. | Description | Give the user an interface to access their inbox.
| Title | Share Thought
| Description | Give user an interface to share a thought outside of the platform.

## ToolsTech
Web

## Project Plan
Backlog | Sprint I |  |  | Begin | 2018-03-08 | Sprint II |  |  | Begin | 2018-03-24 | Sprint III |  |  | Begin | 2018-04-07 | Sprint IV |  |  | Begin | 2018-04-21
|  |  |  | End | 2018-03-22 |  |  |  | End | 2018-04-05 |  |  |  | End | 2018-04-19 |  |  |  | End | 2018-05-03
|  |  |  | Review | 2018-03-22 |  |  |  | Review | 2018-04-05 |  |  |  | Review | 2018-04-19 |  |  |  | Review | 2018-05-03
| Story | Owner/Role | Status | ETA | Note | Story | Owner/Role | Status | ETA | Note | Story | Owner/Role | Status | ETA | Note | Story | Owner/Role | Status | ETA | Note
Mobile App | As a user I can sign up. | Mohamed Ahmed | DONE | 2018-03-15 |  | As a user I can check out my profile. | Mohamed Nada | CLEAR | 2018-03-29 |  | As a user I can see my home with many thoughts. | Mohamed Nada | CLEAR | 2018-04-19
As a user I can login | As a user I can login | Mohamed Farouk | DONE | 2018-03-15 |  | As a user I can edit my about info. | Mohamed Nada | CLEAR | 2018-03-29 |  | As a user I can post a photo. | Mohamed Ahmed | CLEAR | 2018-04-19
As a user I can sign up. | [5 empty] | As a user I can write a thought | Mohamed Ahmed | CLEAR | 2018-03-29
As a user I can see my home with many thoughts. | As a user I can login in this site. | Alaa Obour | DONE | 2018-03-15
As a user I can check out my profile. | As a user I can register to this site. | Mohamed Mohamed Ali | DONE | 2018-03-15 |  | As a user I can see my profile there are thoughts and my profile picture. | Mohamed Mohamed Ali | CLEAR | 2018-03-29 |  | As a user at home page I can see thoughts from people I follow | Mohamed Mohamed Ali | CLEAR | 2018-04-19
As a user I can rethought. | [5 empty] | As a user I can edit the about section on profile page . | Alaa Obour | CLEAR | 2018-03-29 |  | I can like thought. | Alaa Obour | CLEAR | 2018-04-19
As a user I can change app settings. | As a dev I can use an API log a user in. | Mohamed Nada | DONE | 2018-03-15 |  | As a user , I can thought. | Mohamed Mohamed Ali | CLEAR | 2018-03-29
As a user I can edit my about info. | As a dev I can use an API sign a user up. | Mohamed Baz | DONE | 2018-03-15
As a user I can message a friend. | As a user I have all my info in a database eg, (id , name , user name). | Mohamed Farouk | DONE | 2018-03-15 |  | As a dev I can use an API to acess a thought . | Mohamed Farouk | CLEAR | 2018-03-29 |  | As a dev I can use an api to get the a stream of thoughts to show the user. | Mohamed Farouk | CLEAR | 2018-04-19
As a user I can see my inbox. | [5 empty] | As a dev I can use an API to record a thought in the database. | Mohamed Baz | CLEAR | 2018-03-29 |  | As a dev I can access an API update a thought's status (Likes). | Mohamed Baz | CLEAR | 2018-04-19
As a user I can change my password. | [5 empty] | As I user I have my profile's data in a database (username, thoughts, profile picture, about message, etc. | Mohamed Farouk | CLEAR | 2018-03-29
As a user I can post a photo.
As a user I can write a thought
As a user I can reply to a thought
Website
As a user I can put a special profile picture for me.
As a user at home page I can see thoughts from people I follow
As a user I can see my profile there are thoughts and my profile picture.
As a user I can rethought
As a user I can edit the about section on profile page .
As a user I can message a friend .
As a user I can see my inbox.
As a user I can reply on thoughts .
I can like thought.
As a user , I can thought.
As a user I can search for a friend by username
As a user I can follow friends.
As a user I can share a thought.
As a user I can Change my password.
As a user I can login in this site.
As a user I can register to this site.
Backend
As a dev I can use an API to handle follow / unfollow .
As a dev I can use an API to handle to search .
As a dev I can use an API to acess a thought .
As a dev I can use an API to record a thought in the database.
As a dev I can use an api to get the a stream of thoughts to show the user.
As a dev I can use an API log a user in.
As a dev I can use an API sign a user up.
As a dev I can use an API change a user's photo .
As a dev I can access an API update a thought's status (Likes).
As a user I have all my info in a database eg, (id , name , user name).
As I user I have my profile's data in a database (username, thoughts, profile picture, about message, etc.

## Schedule
Schedule | Events
Thu, 1st March | Project setup, conduct research, prepare plan. assign roles.
Thu, 8th March | Sprint I
Thu, 22nd March | Sprint I review meeting
Sat, 24th March | Sprint II
Thu, 5th April | Sprint II review meeting
Sat, 7th April | Sprint III
Thu, 19th April | Sprint III review meeting
Sat, 21st April | Sprint IV
Thu, 3rd May | Sprint IV review meeting

## Feature List
Feature List
Sign up
Sign in
Home stream
User profile
Post a Thought
Profile picture
Update about
Post a Photo
Private messages
Inbox
Reset forgotten password
Reply to a thought
Update Settings
Share link to a Thought

## Requirements
Functional | Non Functional
Login / Register | Facility: Easy to use
Post a thought | Simplicity: Simple Interface
Like A thought | Security: Secure access
See a stream of Thoughts from people I follow | Availablility: Realtime updates
Follow Friends | Speed: No lagging
Messaging